## Sheet1
ADO ID | Work Item Type | Created Date | Feature Title | User Story Title | Assigned To | Request Status | IT Enhancement Number | Customer Name | Iteration Path | Level of Effort | Story Points (0-99) | Value (0-99) | Priority (0-4) | Target Date
32169 | User Story | Wednesday, April 17, 2024 |  | Pena Traffic Data in BI | Anthony | Closed | ENHC0014783 |  | \Hydrangea |  |  |  | 0
32705 | User Story | Monday, June 17, 2024 |  | Load historical data | Anthony | Active | ENHC0014783 |  | \Poppy |  |  |  | 0
32780 | User Story | Thursday, June 20, 2024 |  | Build tabular model | Anthony | Closed | ENHC0014783 |  | \ |  |  |  | 0
33188 | User Story | Thursday, July 25, 2024 |  | Deploy to Prod | Anthony | Closed | ENHC0014783 |  | \Hydrangea |  |  |  | 0
32054 | User Story | Tuesday, April 9, 2024 |  | Modify Service Desk dashboards | Steve | Closed | ENHC0014930 |  | \Dahlia |  |  |  | 0
32308 | User Story | Wednesday, May 1, 2024 |  | Get requirements / scope | Steve | New | ENHC0015035 |  | \ |  |  |  | 0
32168 | User Story | Wednesday, April 17, 2024 |  | Create a list of solutions |  | New | ENHC0015048 |  | \ |  |  |  | 0
32436 | User Story | Friday, May 17, 2024 |  | Outbound Phone calls vendor 1 - update dashboard | Harry | Closed | ENHC0015078 |  | \Sunflower |  |  |  | 0
32438 | User Story | Friday, May 17, 2024 |  | Airport Alarms (update dashboards) | Harry | Closed | ENHC0015078 |  | \Hydrangea |  |  |  | 0
32439 | User Story | Friday, May 17, 2024 |  | Notification System - integration design | Harry | Active | ENHC0015078 |  | \Poppy |  |  |  | 0
32440 | User Story | Friday, May 17, 2024 |  | Notification System - SSIS development |  | New | ENHC0015078 |  | \Carnation |  |  |  | 0
32441 | User Story | Friday, May 17, 2024 |  | Notification System - Tabular model development |  | New | ENHC0015078 |  | \Carnation |  |  |  | 0
32442 | User Story | Friday, May 17, 2024 |  | Notification System - create dashboard |  | New | ENHC0015078 |  | \Carnation |  |  |  | 0
32443 | User Story | Friday, May 17, 2024 |  | Radio calls - update dashboard | Anthony | On Hold | ENHC0015078 |  | \ |  |  |  | 0
32444 | User Story | Friday, May 17, 2024 |  | Crisis Management Software Log Book Entries - requirements | Harry | New | ENHC0015078 |  | \ |  |  |  | 0
32445 | User Story | Friday, May 17, 2024 |  | Crisis Management Software Parking Log Items | Mary | Closed | ENHC0015078 |  | \Hydrangea |  |  |  | 0
32446 | User Story | Friday, May 17, 2024 |  | Teams interactions - requirements | Harry | On Hold | ENHC0015078 |  | \ |  |  |  | 0
33440 | User Story | Tuesday, August 20, 2024 |  | Single data model - Phone Calls data from Vendor 1 and 2 | Steve | Closed | ENHC0015078 |  | \Hydrangea |  |  |  | 0
31870 | User Story | Tuesday, March 26, 2024 |  | Add forecasting capability dashboards |  | New | ENHC0015102 |  | \ |  |  |  | 0
33207 | User Story | Monday, July 29, 2024 |  | Gather requirements |  | New | ENHC0015102 |  | \ |  |  |  | 0
31871 | User Story | Tuesday, March 26, 2024 |  | Add the ability to drill down to that level of granularity of detail |  | New | ENHC0015103 |  | \ |  |  |  | 0
31892 | User Story | Wednesday, March 27, 2024 |  | Create integration for people counter report | Anthony | Closed | ENHC0015114 |  | \Sunflower |  |  |  | 0
32620 | User Story | Thursday, June 6, 2024 |  | Create tabular model for people counter | Mary | Closed | ENHC0015114 |  | \Jasmine |  |  |  | 0
32837 | User Story | Thursday, June 27, 2024 |  | Create dashboard for people counters | Mary | Closed | ENHC0015114 |  | \Jasmine |  |  |  | 0
32314 | User Story | Wednesday, May 1, 2024 |  | Architecture | Rachel | Closed | ENHC0015126 |  | \Zinnia |  |  |  | 0
34459 | User Story | Wednesday, October 23, 2024 |  | Deploy Data Gateway | Anthony | On Hold | ENHC0015126 |  | \Poppy |  |  |  | 0
32419 | User Story | Tuesday, May 14, 2024 |  | Update report | Anthony | Deployment | ENHC0015165 |  | \ |  |  |  | 0
32582 | User Story | Wednesday, June 5, 2024 |  | Load transactions and connect to API | Mary | Closed | ENHC0015171 |  | \Lavender |  |  |  | 0
32552 | User Story | Friday, May 31, 2024 |  | Test connectivity to LogPlan Server | Anthony | Closed | ENHC0015191 |  | \Daffodil |  |  |  | 0
32670 | User Story | Wednesday, June 12, 2024 |  | Extract, transform and load data | Anthony | Awaiting Customer | ENHC0015191 |  | \ |  |  |  | 0
32631 | User Story | Monday, June 10, 2024 |  | Rob to look at the data integration API |  | Closed | ENHC0015195 |  | \ |  |  |  | 0
33125 | User Story | Monday, July 22, 2024 |  | Create SSRS report for ADA Compliant | Harry | On Hold | ENHC0015257 |  | \ |  |  |  | 0
33445 | User Story | Tuesday, August 20, 2024 |  | Research vendor docs and API requirements | Anthony | Closed | ENHC0015292 |  | \Hydrangea |  |  |  | 0
33968 | User Story | Tuesday, September 24, 2024 |  | Develop SSIS integration for Occupancy Data - Near Realtime. | Anthony | New | ENHC0015292 |  | \ |  |  |  | 0
33969 | User Story | Tuesday, September 24, 2024 |  | Update Tabular Model for Transaction Data. | Anthony | New | ENHC0015292 |  | \ |  |  |  | 0
34406 | User Story | Friday, October 18, 2024 |  | Maintenance source - Review technical document | Mary | Closed | ENHC0015327 |  | \Poppy |  |  |  | 0
34463 | User Story | Wednesday, October 23, 2024 |  | Crisis Management Source- Snow requirements gathering | Mary | New | ENHC0015413 |  | \Poppy |  |  |  | 0
30707 | User Story | Thursday, January 4, 2024 |  | Compost and Trash Data Integration | Mary | Closed | ENHC0014124 |  | \Hibiscus |  |  |  | 0
30712 | User Story | Thursday, January 4, 2024 |  | User training on the Greenhouse dashboard | Mary | Closed | ENHC0014124 |  | \Hibiscus |  |  |  | 0
30796 | User Story | Friday, January 12, 2024 |  | Jet Fuel Data | Mary | Closed | ENHC0014124 |  | \Gardenia |  |  |  | 0
30797 | User Story | Friday, January 12, 2024 |  | Propane Gas Data | Mary | Closed | ENHC0014124 |  | \Gardenia |  |  |  | 0
31041 | User Story | Thursday, January 25, 2024 |  | Update Energy dashboards to remove Inforiver formatting | Mary | Closed | ENHC0014124 |  | \Orchid |  |  |  | 0
31241 | User Story | Tuesday, February 6, 2024 |  | Combine all fuel sources into one dashboard | Mary | Closed | ENHC0014124 |  | \Gardenia |  |  |  | 0
31893 | User Story | Wednesday, March 27, 2024 |  | Build Emission Dashboard | Mary | Closed | ENHC0014124 |  | \Orchid |  |  |  | 0
29299 | User Story | Thursday, August 10, 2023 |  | Development | Steve | Closed | ENHC0014775 |  | \Jasmine |  |  |  | 0
30097 | User Story | Monday, November 13, 2023 |  | Scoping - Power BI dashboard for Network devices age | Mel | Closed | ENHC0014909 |  | \Hibiscus |  |  |  | 0
30789 | User Story | Thursday, January 11, 2024 |  | Network Device Age - Build Dashboard | Mary | Closed | ENHC0014909 |  | \Dahlia |  |  |  | 0
30986 | User Story | Tuesday, January 23, 2024 |  | Updates to concessions gross sales | Anthony | Closed | ENHC0014911 |  | \ |  |  |  | 0
32541 | User Story | Wednesday, May 29, 2024 |  | Deploy to Prod | Anthony | Closed | ENHC0014911 |  | \Lavender |  |  |  | 0
32688 | User Story | Thursday, June 13, 2024 |  | Research / Gather Requirements | Harry | Closed | ENHC0015094 |  | \Lavender |  |  |  | 0
32540 | User Story | Wednesday, May 29, 2024 |  | Pull data into the warehouse | Mary | Closed | ENHC0015163 |  | \Dahlia |  |  |  | 0
32702 | User Story | Monday, June 17, 2024 |  | UAT - Parking stats | Mary | Closed | ENHC0015163 |  | \Daffodil |  |  |  | 0
32813 | User Story | Tuesday, June 25, 2024 |  | Production Deployment - Parking Stats | Mary | Closed | ENHC0015163 |  | \Daffodil |  |  |  | 0
32358 | User Story | Tuesday, May 7, 2024 |  | Add additional dashboards | Mary | Closed | ENHC0015169 |  | \Tulip |  |  |  | 0
32417 | User Story | Tuesday, May 14, 2024 |  | Maintenance Software connectivity testing | Steve | Closed | ENHC0015179 |  | \Dahlia |  |  |  | 0
33446 | User Story | Tuesday, August 20, 2024 |  | Complete Tutorials | Steve | Closed | ENHC0015218 |  | \Hydrangea |  |  |  | 0
33447 | User Story | Tuesday, August 20, 2024 |  | Complete Tutorials | Anthony | Closed | ENHC0015218 |  | \Hydrangea |  |  |  | 0
33448 | User Story | Tuesday, August 20, 2024 |  | Complete Tutorials | Mary | Closed | ENHC0015218 |  | \Hydrangea |  |  |  | 0
33449 | User Story | Tuesday, August 20, 2024 |  | Complete Tutorials | Harry | Closed | ENHC0015218 |  | \Hydrangea |  |  |  | 0
33683 | User Story | Friday, September 6, 2024 |  | ML workshop |  | Closed | ENHC0015218 |  | \Lavender |  |  |  | 0
33684 | User Story | Friday, September 6, 2024 |  | GenAI workshop |  | Closed | ENHC0015218 |  | \Lavender |  |  |  | 0
33329 | User Story | Friday, August 9, 2024 |  | Microsoft Purview POC - Data Quality | Rachel | Closed | ENHC0015220 |  | \Hydrangea |  |  |  | 0
33012 | User Story | Monday, July 15, 2024 |  | Research | Mary | Closed | ENHC0015249 |  | \Jasmine |  |  |  | 0
33330 | User Story | Friday, August 9, 2024 |  | Cash Posting Finance source | Steve | Closed | ENHC0015273 |  | \Hydrangea |  |  |  | 0
34220 | User Story | Monday, October 7, 2024 |  | Service Desk cross training | Steve | New | ENHC0014930 |  | \ |  |  |  | 1
26601 | User Story | Friday, July 1, 2022 |  | Greenhouse Gas Emissions Dashboard | Mary | Closed | ENHC0014124 |  | \Chrysanthemum |  |  |  | 2
26603 | User Story | Friday, July 1, 2022 |  | Energy Sustainability Dashboard | Mary | Closed | ENHC0014126 |  | \ |  |  |  | 2
30708 | User Story | Thursday, January 4, 2024 |  | Finance Source - Develop to pull compensation rates | Anthony | On Hold | ENHC0014455 |  | \Poppy |  | 20 |  | 0
34166 | User Story | Wednesday, October 2, 2024 |  | Concession - Transactions Count Demo & UAT | Mary | Active | ENHC0015171 |  | \Poppy |  | 4 |  | 0
34653 | User Story | Wednesday, November 6, 2024 |  | Develop SSIS integration | Steve | Active | ENHC0015195 |  | \Poppy |  | 10 |  | 0
34219 | User Story | Monday, October 7, 2024 |  | Provide advice to Procurement software | Steve | Closed | ENHC0015288 |  | \Zinnia |  | 2 |  | 0
32413 | User Story | Tuesday, May 14, 2024 |  | Research data | Anthony | Closed | ENHC0015163 |  | \Tulip |  | 1 |  | 0
33578 | User Story | Thursday, August 29, 2024 |  | Fix / enhance Service Desk dashboards | Steve | Active | ENHC0014930 |  | \Poppy |  | 10 | 1 | 0
32437 | User Story | Friday, May 17, 2024 |  | Phone Calls Vendor 2 - update dashboard | Harry | Active | ENHC0015078 |  | \Poppy |  | 8 | 16 | 0
34117 | User Story | Monday, September 30, 2024 |  | SSIS integration from Sharepoint to data gateway | Anthony | Closed | ENHC0015126 |  | \Zinnia |  | 16 | 20 | 0
33275 | User Story | Monday, August 5, 2024 |  | Gathering requirements | Steve | Closed | ENHC0015195 |  | \Lavender |  |  | 4 | 0
34517 | User Story | Thursday, October 24, 2024 |  | Expand people counter data | Steve | Closed | ENHC0015195 |  | \Poppy |  | 5 | 5 | 0
34168 | User Story | Wednesday, October 2, 2024 |  | Gather Fuel requirements | Rachel | New | ENHC0015258 |  | \Poppy |  | 2 | 0 | 0
33899 | User Story | Friday, September 20, 2024 |  | Map parking data file to existing parking table. | Anthony | Closed | ENHC0015292 |  | \Lavender |  |  | 4 | 0
33967 | User Story | Tuesday, September 24, 2024 |  | Parking - Update SSIS Integration for Daily Transaction Data. | Anthony | Active | ENHC0015292 |  | \Poppy |  | 30 | 10 | 0
34114 | User Story | Monday, September 30, 2024 |  | Workflow data Integration from Crisis Management Software Workflow | Mary | On Hold | ENHC0015314 |  | \ |  | 40 | 10 | 0
34589 | User Story | Thursday, October 31, 2024 |  | Maven Sprint 2 development | Mary | Active | ENHC0015327 |  | \Poppy |  | 160 | 16 | 0
34464 | User Story | Wednesday, October 23, 2024 |  | Airport Ops - Research existing FIDS reports and requirements | Anthony | Active | ENHC0015432 |  | \Poppy |  | 4 | 2 | 0
33996 | User Story | Thursday, September 26, 2024 |  | Development - ADA Vendor 1 Automation | Harry | Closed | ENHC0015094 |  | \Zinnia |  | 5 | 5 | 0
34103 | User Story | Monday, September 30, 2024 |  | Development - ADA Vendor 2 Automation | Harry | Closed | ENHC0015094 |  | \Zinnia |  | 10 | 10 | 0
34104 | User Story | Monday, September 30, 2024 |  | Development - ADA Kiosks Automation | Harry | Closed | ENHC0015094 |  | \Zinnia |  | 20 | 25 | 0
34105 | User Story | Monday, September 30, 2024 |  | Development - ADA Vendor 3 Automation | Harry | Closed | ENHC0015094 |  | \Zinnia |  | 20 | 15 | 0
17021 | Feature | Monday, July 1, 2019 | Add UMD for "full de-ice event" dates into flight model |  |  | New | ENHC0010862 | Matthew Broderick | \ | Medium |  |  | 2
27621 | Feature | Thursday, February 2, 2023 | Compensation rates are not populating in Concessions reports. |  | Anthony | Active | ENHC0014455 | Branden Flowers | \ |  |  |  | 2
28848 | Feature | Tuesday, June 20, 2023 | Migrate Pena traffic data from source to prod |  | Anthony | On Hold | ENHC0014783 | Chelesa Clinton | \ | Medium
29038 | Feature | Wednesday, July 19, 2023 | FCR (fist contact resolution) Service now report and power BI dashboard. |  |  | New | ENHC0014828 | Jake From StateFarm | \ |  |  |  | 4
30022 | Feature | Thursday, November 2, 2023 | Service Desk dashboards |  | Steve | Active | ENHC0014930 | Jake From StateFarm | \ | High |  |  | 2 | Sunday, May 12, 2024
30600 | Feature | Thursday, December 28, 2023 | Pena Crash Data |  |  | On Hold | ENHC0014973 | Lisa Bonet | \ |  |  |  | 4
30795 | Feature | Friday, January 12, 2024 | Shuttle Reports based on data reporting system |  |  | New | ENHC0015005 | Bryan Adams | \
31125 | Feature | Wednesday, January 31, 2024 | Controls project |  |  | On Hold | ENHC0015035 | Larry Wilmore | \
31231 | Feature | Monday, February 5, 2024 | DEN Commercial Dashboard 2.0 |  |  | New | ENHC0015044 | Tina Fey | \
31264 | Feature | Thursday, February 8, 2024 | Connectors Migration |  |  | New | ENHC0015048 | Rebecca DeMornay | \
31266 | Feature | Friday, February 9, 2024 | Connect to an external weather dataset for our Snow Dashboards probably via API to help our team better tell the story about runway downtime. |  |  | New | ENHC0015051 | Tracy Chapman | \ |  |  |  | 2
31483 | Feature | Monday, February 26, 2024 | Update to Maintenance database |  |  | New | ENHC0015069 | Tracy Chapman | \
31596 | Feature | Friday, March 1, 2024 | New measure for train system |  |  | New | ENHC0014906 | Matthew Broderick | \
31603 | Feature | Friday, March 1, 2024 | Comms Center Dashboard |  |  | Active | ENHC0015078 | Tracy Chapman | \
31651 | Feature | Friday, March 8, 2024 | OPs Security Screening Occupancy Reporting |  |  | New | ENHC0015091 | Tracy Chapman | \
31827 | Feature | Monday, March 18, 2024 | Parking - Add Forecasting capability to Parking and Transportation dashboards |  |  | New | ENHC0015102 | Bryan Adams | \
31828 | Feature | Monday, March 18, 2024 | Parking - Rideshare 10 or 15 min granular level of detail |  |  | New | ENHC0015103 | Bryan Adams | \
31884 | Feature | Tuesday, March 26, 2024 | Create platform people counter report |  | Anthony | On Hold | ENHC0015114 | Nate Bargatze | \
32064 | Feature | Wednesday, April 10, 2024 | Procurement Opportunities to Flydenver API Gateway |  |  | Active | ENHC0015126 | Michelle Obama | \
32323 | Feature | Friday, May 3, 2024 | Update SSRS Business Directory Report to be ADA Complaint. |  |  | On Hold | ENHC0015165 | Michelle Obama | \ |  |  |  | 2
32363 | Feature | Wednesday, May 8, 2024 | Parking - Lost and Found Dashboard |  |  | New | ENHC0015170 | Mark Cuban | \
32364 | Feature | Wednesday, May 8, 2024 | Capture concessionaire transaction data in the concessions warehouse. |  |  | Active | ENHC0015171 | Branden Flowers | \
32519 | Feature | Thursday, May 23, 2024 | Baggage Handling System data into the DEN Data Warehouse |  |  | On Hold | ENHC0015191 | Matthew Broderick | \
32531 | Feature | Wednesday, May 29, 2024 | Expanding the data that is being passed to us from People counter source via API |  | Steve | Active | ENHC0015195 | Tracy Chapman | \
32669 | Feature | Wednesday, June 12, 2024 | Request Reports on People counter data |  |  | New | ENHC0015215 | Robert Downey | \
32907 | Feature | Wednesday, July 3, 2024 | Concessions gross sales report - ADA compliant |  |  | On Hold | ENHC0015247 | Lawrence Taylor | \
33011 | Feature | Monday, July 15, 2024 | Update Airline stats SSRS report to be ADA Compliant. |  |  | On Hold | ENHC0015257 | George Clooney | \
33013 | Feature | Tuesday, July 16, 2024 | Add Search for the Fuel form and process |  |  | New | ENHC0015258 | Steve Martin | \ |  |  |  | 2
33034 | Feature | Tuesday, July 16, 2024 | Non-Production Network Production/Inventory Values and Cost Estimation sheets need adjusting/correcting (use attached docs) |  |  | New | ENHC0015259 | Travis Barker | \
33335 | Feature | Friday, August 9, 2024 | Add procurement data to data warehouse |  |  | On Hold | ENHC0015288 | Eliot Page | \
33367 | Feature | Tuesday, August 13, 2024 | Parking Data coming online from Contractor |  | Anthony | Active | ENHC0015292 | Bryan Adams | \ |  |  |  | 2
33706 | Feature | Monday, September 9, 2024 | Crisis Management Workflow API Call Proof of Concept/Documentation |  |  | On Hold | ENHC0015314 | Michael Myers | \Lavender
33880 | Feature | Thursday, September 19, 2024 | Updates to Concession Incentive Program |  |  | New | ENHC0015326 | Lawrence Taylor | \
33897 | Feature | Friday, September 20, 2024 | Review and update DW due to 'decustomizing' Maintnance source fields / Maintenance source reimplementation |  | Rachel | Active | ENHC0015327 |  | \
33977 | Feature | Tuesday, September 24, 2024 | Create new data fields in Maintenance Data warehouse |  |  | New | ENHC0015351 |  | \
34314 | Feature | Thursday, October 10, 2024 | Add concourse to Flight Schedule Analytical tabular model |  |  | New | ENHC0015381 | Tracy Chapman | \
34334 | Feature | Monday, October 14, 2024 | PowerBI query from Finance Source |  |  | New | ENHC0015409 | Lawrence Taylor | \ |  |  |  | 2
34347 | Feature | Tuesday, October 15, 2024 | Add a field to the Employee Extract file in the Database |  |  | New | ENHC0015410 | Renee Zellwegger | \
34372 | Feature | Tuesday, October 15, 2024 | We need all of the Snow data from Crisis Management source moved into the Data Warehouse |  | Mary | Active | ENHC0015413 | Tracy Chapman | \ |  |  |  | 2
34410 | Feature | Friday, October 18, 2024 | Snow Deactivation data model from source to Power BI for DEN Snow Dashboard |  |  | New | ENHC0015418 | Derek Henry | \
34433 | Feature | Monday, October 21, 2024 | Pull regulation data submissions into database so GIS team can access the data |  |  | New | ENHC0015425 | Chelesa Clinton | \
34434 | Feature | Monday, October 21, 2024 | Biometric Exit dashboard request |  |  | New | ENHC0015426 |  | \
34436 | Feature | Tuesday, October 22, 2024 | In the Service Request Data Warehouse, need the "SENT TO" field created |  |  | New | ENHC0015428 | Matthew Broderick | \
34457 | Feature | Wednesday, October 23, 2024 | Airport ops data extract to DEN BI data warehouse |  | Anthony | Active | ENHC0015432 | Robert Downey | \
34568 | Feature | Wednesday, October 30, 2024 | CNG Crisis Management report |  | Mary | Active | ENHC0015443 | Bryan Adams | \
34586 | Feature | Thursday, October 31, 2024 | Load Screening Q3 data |  | Steve | Active | ENHC0015449 | James Murray | \Poppy
34587 | Feature | Thursday, October 31, 2024 | Insurance data to Power BI |  | Steve | Active | ENHC0015450 | Derek Henry | \Poppy
34588 | Feature | Thursday, October 31, 2024 | Products data cleanup |  | Steve | Active | ENHC0015451 | Lonnie Anderson | \Poppy
28052 | Feature | Wednesday, March 22, 2023 | Sustainability Dashboards |  | Mary | Closed | ENHC0014124 |  | \ |  |  |  | 2
28806 | Feature | Monday, June 12, 2023 | Upgrade to latest version - Connector 1 |  | Steve | Closed | ENHC0014775 | Rebecca DeMornay | \Jasmine
29793 | Feature | Thursday, October 5, 2023 | Power BI dashboard for Network devices age |  |  | Closed | ENHC0014909 | Michael Keaton | \
29816 | Feature | Monday, October 9, 2023 | Updates to concessions gross sales |  | Anthony | Closed | ENHC0014911 | Lawrence Taylor | \ | Medium
31710 | Feature | Tuesday, March 12, 2024 | ADA Monthly Service Reports Automation |  |  | Closed | ENHC0015094 | Renee Zellwegger | \
32321 | Feature | Thursday, May 2, 2024 | We need to pull data from the parking vendor into the data warehouse to enable regular reporting on Parking Lot Capacity |  |  | Closed | ENHC0015163 | Tracy Chapman | \Tulip |  |  |  |  | Sunday, May 12, 2024
32338 | Feature | Tuesday, May 7, 2024 | Self Bagdrop Dashboard Enhancement |  |  | Closed | ENHC0015169 | Nate Bargatze | \
32416 | Feature | Tuesday, May 14, 2024 | Maintenance software rehosting testing |  |  | Closed | ENHC0015179 | Russell Peters | \
32536 | Feature | Wednesday, May 29, 2024 | Add Previous Week Page Report to OPS Ramp Tower Metrics |  |  | Closed | ENHC0015196 |  | \
32537 | Feature | Wednesday, May 29, 2024 | OPS On Time Performance Report |  |  | Closed | ENHC0015197 |  | \
32538 | Feature | Wednesday, May 29, 2024 | OPS TSA Checkpoint Wait Times |  |  | Closed | ENHC0015198 |  | \
32691 | Feature | Thursday, June 13, 2024 | Microsoft Fabric POC |  |  | Closed | ENHC0015218 | Chris Martin | \
32692 | Feature | Thursday, June 13, 2024 | Microsoft Purview POC - Data Quality |  |  | Closed | ENHC0015220 | Chris Martin | \
32964 | Feature | Tuesday, July 9, 2024 | AskIT/ServiceNow fields imported into the Data Warehouse. |  |  | Closed | ENHC0015249 | Renee Zellwegger | \
33218 | Feature | Wednesday, July 31, 2024 | BI reports from Finance source for cash posting |  |  | Closed | ENHC0015273 | Michael Douglas | \
34315 | Feature | Thursday, October 10, 2024 | Maintenance Division data collection and analysis for Q3/V.100 |  |  | Closed | ENHC0015382 |  | \
34316 | Feature | Thursday, October 10, 2024 | Maintenance Division data analytics for Q3/Vision100 |  |  | Closed | ENHC0015387 |  | \