## Sheet1
Enhancement ID | Requested On | Last Updated Date | Developer Working on Request | Manager | Azure Devops ID | Work Item Type | Created Date | Feature Title | User Story Title | Request Status | Customer Name | Iteration Path | Level of Effort | Story Points (0-99) | Value (0-99) | Target Date | Priority
ENHC0015273 | 2024-07-30 | 2024-10-24 | steven | Lukas | 33330 | User Story | Friday, August 9, 2024 |  | Cash Posting Finance source | Closed | steve martin | \Hydrangea | Easy | 44 | 44 |  | Low
ENHC0015273 | 2024-07-30 | 2024-10-24 | steven | Daniel | 33218 | Feature | Wednesday, July 31, 2024 | BI reports from Finance source for cash posting |  | Closed | michael douglas | \ | Easy | 47 | 47 |  | High
ENHC0015220 | 2024-06-13 | 2024-09-04 | rachel | Lukas | 33329 | User Story | Friday, August 9, 2024 |  | Microsoft Purview POC - Data Quality | Closed | lonnie anderson | \Hydrangea | Medium | 64 | 64 |  | Low
ENHC0015220 | 2024-06-13 | 2024-09-04 | rachel | Daniel | 32692 | Feature | Thursday, June 13, 2024 | Microsoft Purview POC - Data Quality |  | Closed | chris martin | \ | Medium | 67 | 67 |  | Low
ENHC0014911 | 2023-10-09 | 2024-10-25 | anthony | Daniel | 30986 | User Story | Tuesday, January 23, 2024 |  | Updates to concessions gross sales | Closed | eliot page | \ | Medium | 67 | 67 |  | Low
ENHC0014911 | 2023-10-09 | 2024-10-25 | anthony | Connor | 32541 | User Story | Wednesday, May 29, 2024 |  | Deploy to Prod | Closed | lawrence taylor | \Lavender | Easy | 9 | 9 |  | Low
ENHC0014911 | 2023-10-09 | 2024-10-25 | anthony | Lukas | 29816 | Feature | Monday, October 9, 2023 | Updates to concessions gross sales |  | Closed | lawrence taylor | \ | Hard | 83 | 83 |  | High
ENHC0015169 | 2024-05-07 | 2024-06-11 | mary | Connor | 32358 | User Story | Tuesday, May 7, 2024 |  | Add additional dashboards | Closed | matthew broderick | \Tulip | Easy | 21 | 21 |  | Low
ENHC0015169 | 2024-05-07 | 2024-06-11 | mary | Lukas | 32338 | Feature | Tuesday, May 7, 2024 | Self Bagdrop Dashboard Enhancement |  | Closed | nate bargatze | \ | Easy | 36 | 36 |  | High
ENHC0014775 | 2023-06-12 | 2024-09-30 | steven | Lukas | 29299 | User Story | Thursday, August 10, 2023 |  | Development | Closed | matthew broderick | \Jasmine | Hard | 87 | 87 |  | Low
ENHC0014775 | 2023-06-12 | 2024-09-30 | steven | Lukas | 28806 | Feature | Monday, June 12, 2023 | Upgrade to latest version - Connector 1 |  | Closed | rebecca demornay | \Jasmine | Medium | 70 | 70 |  | High
ENHC0015249 | 2024-07-09 | 2024-09-10 | mel | Connor | 33012 | User Story | Monday, July 15, 2024 |  | Research | Closed | michelle obama | \Jasmine | Hard | 88 | 88 |  | Low
ENHC0015249 | 2024-07-09 | 2024-09-10 | mel | Daniel | 32964 | Feature | Tuesday, July 9, 2024 | AskIT/ServiceNow fields imported into the Data Warehouse. |  | Closed | renee zellwegger | \ | Hard | 88 | 88 |  | Low
ENHC0015094 | 2024-03-12 | 2024-10-25 | rachel | Connor | 32688 | User Story | Thursday, June 13, 2024 |  | Research / Gather Requirements | Closed | robert downey | \Lavender | Easy | 12 | 12 |  | Low
ENHC0015094 | 2024-03-12 | 2024-10-25 | rachel | Connor | 33996 | User Story | Thursday, September 26, 2024 |  | Development - ADA Vendor 1 Automation | Closed | larry wilmore | \Zinnia | Easy | 5 | 5 |  | Low
ENHC0015094 | 2024-03-12 | 2024-10-25 | rachel | Lukas | 34103 | User Story | Monday, September 30, 2024 |  | Development - ADA Vendor 2 Automation | Closed | eliot page | \Zinnia | Easy | 10 | 10 |  | Low
ENHC0015094 | 2024-03-12 | 2024-10-25 | rachel | Daniel | 34104 | User Story | Monday, September 30, 2024 |  | Development - ADA Kiosks Automation | Closed | mark cuban | \Zinnia | Easy | 20 | 25 |  | Low
ENHC0015094 | 2024-03-12 | 2024-10-25 | rachel | Daniel | 34105 | User Story | Monday, September 30, 2024 |  | Development - ADA Vendor 3 Automation | Closed | derek henry | \Zinnia | Easy | 20 | 15 |  | Low
ENHC0015094 | 2024-03-12 | 2024-10-25 | rachel | Daniel | 31710 | Feature | Tuesday, March 12, 2024 | ADA Monthly Service Reports Automation |  | Closed | renee zellwegger | \ | Medium | 58 | 58 |  | High
ENHC0015179 | 2024-05-14 | 2024-07-09 | steven | Daniel | 32417 | User Story | Tuesday, May 14, 2024 |  | Maintenance Software connectivity testing | Closed | michael keaton | \Dahlia | Medium | 65 | 65 |  | Low
ENHC0015179 | 2024-05-14 | 2024-07-09 | steven | Lukas | 32416 | Feature | Tuesday, May 14, 2024 | Maintenance software rehosting testing |  | Closed | russell peters | \ | Easy | 39 | 39 |  | Low
ENHC0014909 | 2023-10-05 | 2024-07-10 | mary | Daniel | 30097 | User Story | Monday, November 13, 2023 |  | Scoping - Power BI dashboard for Network devices age | Closed | jake from statefarm | \Hibiscus | Hard | 87 | 87 |  | Low
ENHC0014909 | 2023-10-05 | 2024-07-10 | mary | Lukas | 30789 | User Story | Thursday, January 11, 2024 |  | Network Device Age - Build Dashboard | Closed | russell peters | \Dahlia | Easy | 46 | 46 |  | Low
ENHC0014909 | 2023-10-05 | 2024-07-10 | mary | Lukas | 29793 | Feature | Thursday, October 5, 2023 | Power BI dashboard for Network devices age |  | Closed | michael keaton | \ | Hard | 88 | 88 |  | High
ENHC0015163 | 2024-05-02 | 2024-06-28 | mary | Daniel | 32540 | User Story | Wednesday, May 29, 2024 |  | Pull data into the warehouse | Closed | russell peters | \Dahlia | Hard | 81 | 81 |  | Low
ENHC0015163 | 2024-05-02 | 2024-06-28 | mary | Connor | 32702 | User Story | Monday, June 17, 2024 |  | UAT - Parking stats | Closed | steve martin | \Daffodil | Easy | 37 | 37 |  | Low
ENHC0015163 | 2024-05-02 | 2024-06-28 | mary | Lukas | 32813 | User Story | Tuesday, June 25, 2024 |  | Production Deployment - Parking Stats | Closed | bryan adams | \Daffodil | Easy | 25 | 25 |  | Low
ENHC0015163 | 2024-05-02 | 2024-06-28 | mary | Connor | 32413 | User Story | Tuesday, May 14, 2024 |  | Research data | Closed | jake from statefarm | \Tulip | Easy | 1 | 77 |  | Low
ENHC0015163 | 2024-05-02 | 2024-06-28 | mary | Lukas | 32321 | Feature | Thursday, May 2, 2024 | We need to pull data from the parking vendor into the data warehouse to enable regular reporting on Parking Lot Capacity |  | Closed | tracy chapman | \Tulip | Hard | 77 | 72 | Sunday, May 12, 2024 | Low
ENHC0015432 | 2024-10-23 | 2024-10-25 | anthony | Daniel | 34464 | User Story | Wednesday, October 23, 2024 |  | Airport Ops - Research existing FIDS reports and requirements | Active | michelle obama | \Poppy | Easy | 4 | 2 |  | Low
ENHC0015432 | 2024-10-23 | 2024-10-25 | anthony | Daniel | 34457 | Feature | Wednesday, October 23, 2024 | Airport ops data extract to DEN BI data warehouse |  | Active | robert downey | \ | Medium | 72 | 9 |  | Low
ENHC0015413 | 2024-10-15 | 2024-10-24 | mary | Connor | 34463 | User Story | Wednesday, October 23, 2024 |  | Crisis Management Source- Snow requirements gathering | New | michael keaton | \Poppy | Easy | 9 | 20 |  | Low
ENHC0015413 | 2024-10-15 | 2024-10-24 | mary | Lukas | 34372 | Feature | Tuesday, October 15, 2024 | We need all of the Snow data from Crisis Management source moved into the Data Warehouse |  | Active | tracy chapman | \ | Easy | 20 | 80 |  | Low
ENHC0015351 | 2024-09-24 | 2024-09-24 | mel | Daniel | 33977 | Feature | Tuesday, September 24, 2024 | Create new data fields in Maintenance Data warehouse |  | New | james murray | \ | Hard | 80 | 69 |  | High
ENHC0015327 | 2024-09-20 | 2024-10-25 | rachel | Daniel | 34406 | User Story | Friday, October 18, 2024 |  | Maintenance source - Review technical document | Closed | russell peters | \Poppy | Medium | 69 | 79 |  | Low
ENHC0015327 | 2024-09-20 | 2024-10-25 | rachel | Daniel | 34589 | User Story | Thursday, October 31, 2024 |  | Maven Sprint 2 development | Active | michael douglas | \Poppy | Hard | 160 | 16 |  | Low
ENHC0015327 | 2024-09-20 | 2024-10-25 | rachel | Lukas | 33897 | Feature | Friday, September 20, 2024 | Review and update DW due to 'decustomizing' Maintnance source fields / Maintenance source reimplementation |  | Active | branden flowers | \ | Hard | 79 | 47 |  | Low
ENHC0015215 | 2024-06-12 | 2024-10-09 | harry | Connor | 32669 | Feature | Wednesday, June 12, 2024 | Request Reports on People counter data |  | New | robert downey | \ | Easy | 47 | 64 |  | Low
ENHC0015171 | 2024-05-08 | 2024-09-19 | mel | Lukas | 32582 | User Story | Wednesday, June 5, 2024 |  | Load transactions and connect to API | Closed | travis barker | \Lavender | Medium | 64 | 82 |  | Low
ENHC0015171 | 2024-05-08 | 2024-09-19 | mel | Connor | 34166 | User Story | Wednesday, October 2, 2024 |  | Concession - Transactions Count Demo & UAT | Active | tina fey | \Poppy | Easy | 4 | 99 |  | Low
ENHC0015171 | 2024-05-08 | 2024-09-19 | mel | Connor | 32364 | Feature | Wednesday, May 8, 2024 | Capture concessionaire transaction data in the concessions warehouse. |  | Active | branden flowers | \ | Hard | 82 | 88 |  | Low
ENHC0014455 | 2023-02-02 | 2024-05-29 | anthony | Lukas | 30708 | User Story | Thursday, January 4, 2024 |  | Finance Source - Develop to pull compensation rates | On Hold | chelesa clinton | \Poppy | Easy | 20 | 49 |  | Low
ENHC0014455 | 2023-02-02 | 2024-05-29 | anthony | Connor | 27621 | Feature | Thursday, February 2, 2023 | Compensation rates are not populating in Concessions reports. |  | Active | branden flowers | \ | Hard | 99 | 29 |  | Low
ENHC0015292 | 2024-08-13 | 2024-10-24 | anthony | Lukas | 33445 | User Story | Tuesday, August 20, 2024 |  | Research vendor docs and API requirements | Closed | robert downey | \Hydrangea | Hard | 88 | 19 |  | Low
ENHC0015292 | 2024-08-13 | 2024-10-24 | anthony | Lukas | 33968 | User Story | Tuesday, September 24, 2024 |  | Develop SSIS integration for Occupancy Data - Near Realtime. | New | george clooney | \ | Easy | 49 | 19 |  | Low
ENHC0015292 | 2024-08-13 | 2024-10-24 | anthony | Lukas | 33969 | User Story | Tuesday, September 24, 2024 |  | Update Tabular Model for Transaction Data. | New | larry wilmore | \ | Easy | 29 | 14 |  | Low
ENHC0015292 | 2024-08-13 | 2024-10-24 | anthony | Daniel | 33899 | User Story | Friday, September 20, 2024 |  | Map parking data file to existing parking table. | Closed | michael myers | \Lavender | Easy | 19 | 4 |  | Low
ENHC0015292 | 2024-08-13 | 2024-10-24 | anthony | Daniel | 33967 | User Story | Tuesday, September 24, 2024 |  | Parking - Update SSIS Integration for Daily Transaction Data. | Active | larry wilmore | \Poppy | Easy | 30 | 10 |  | Low
ENHC0015292 | 2024-08-13 | 2024-10-24 | anthony | Connor | 33367 | Feature | Tuesday, August 13, 2024 | Parking Data coming online from Contractor |  | Active | bryan adams | \ | Easy | 19 | 39 |  | Low
ENHC0015103 | 2024-03-18 | 2024-09-19 | harry | Lukas | 31871 | User Story | Tuesday, March 26, 2024 |  | Add the ability to drill down to that level of granularity of detail | New | branden flowers | \ | Easy | 14 | 32 |  | Low
ENHC0015103 | 2024-03-18 | 2024-09-19 | mel | Lukas | 31828 | Feature | Monday, March 18, 2024 | Parking - Rideshare 10 or 15 min granular level of detail |  | New | bryan adams | \ | Easy | 39 | 65 |  | Low
ENHC0015102 | 2024-03-18 | 2024-09-19 | harry | Daniel | 31870 | User Story | Tuesday, March 26, 2024 |  | Add forecasting capability dashboards | New | lonnie anderson | \ | Easy | 32 | 9 |  | Low
ENHC0015102 | 2024-03-18 | 2024-09-19 | harry | Lukas | 33207 | User Story | Monday, July 29, 2024 |  | Gather requirements | New | lonnie anderson | \ | Medium | 65 | 57 |  | Low
ENHC0015102 | 2024-03-18 | 2024-09-19 | harry | Daniel | 31827 | Feature | Monday, March 18, 2024 | Parking - Add Forecasting capability to Parking and Transportation dashboards |  | New | bryan adams | \ | Easy | 9 | 32 |  | Low
ENHC0015005 | 2024-01-12 | 2024-01-29 | anthony | Connor | 30795 | Feature | Friday, January 12, 2024 | Shuttle Reports based on data reporting system |  | New | bryan adams | \ | Medium | 57 | 31 |  | Low
ENHC0015425 | 2024-10-21 | 2024-10-21 | harry | Connor | 34433 | Feature | Monday, October 21, 2024 | Pull regulation data submissions into database so GIS team can access the data |  | New | chelesa clinton | \ | Easy | 32 | 74 |  | Low
ENHC0014783 | 2023-06-20 | 2024-10-08 | anthony | Lukas | 32169 | User Story | Wednesday, April 17, 2024 |  | Pena Traffic Data in BI | Closed | lawrence taylor | \Hydrangea | Easy | 31 | 23 |  | Low
ENHC0014783 | 2023-06-20 | 2024-10-08 | anthony | Daniel | 32705 | User Story | Monday, June 17, 2024 |  | Load historical data | Active | mark cuban | \Poppy | Medium | 74 | 35 |  | Low
ENHC0014783 | 2023-06-20 | 2024-10-08 | anthony | Daniel | 32780 | User Story | Thursday, June 20, 2024 |  | Build tabular model | Closed | matthew broderick | \ | Easy | 23 | 75 |  | Low
ENHC0014783 | 2023-06-20 | 2024-10-08 | anthony | Daniel | 33188 | User Story | Thursday, July 25, 2024 |  | Deploy to Prod | Closed | russell peters | \Hydrangea | Easy | 35 | 55 |  | Low
ENHC0014783 | 2023-06-20 | 2024-10-08 | anthony | Daniel | 28848 | Feature | Tuesday, June 20, 2023 | Migrate Pena traffic data from source to prod |  | On Hold | chelesa clinton | \ | Medium | 75 | 28 |  | High
ENHC0015418 | 2024-10-18 | 2024-10-18 | harry | Connor | 34410 | Feature | Friday, October 18, 2024 | Snow Deactivation data model from source to Power BI for DEN Snow Dashboard |  | New | derek henry | \ | Medium | 55 | 34 |  | High
ENHC0015288 | 2024-08-09 | 2024-10-16 | harry | Connor | 34219 | User Story | Monday, October 7, 2024 |  | Provide advice to Procurement software | Closed | michael douglas | \Zinnia | Easy | 2 | 0 |  | Low
ENHC0015288 | 2024-08-09 | 2024-10-16 | harry | Connor | 33335 | Feature | Friday, August 9, 2024 | Add procurement data to data warehouse |  | On Hold | eliot page | \ | Easy | 28 | 0 |  | Low
ENHC0015257 | 2024-07-15 | 2024-10-17 | harry | Lukas | 33125 | User Story | Monday, July 22, 2024 |  | Create SSRS report for ADA Compliant | On Hold | larry wilmore | \ | Easy | 34 | 36 |  | Low
ENHC0015257 | 2024-07-15 | 2024-10-17 | harry | Connor | 33011 | Feature | Monday, July 15, 2024 | Update Airline stats SSRS report to be ADA Compliant. |  | On Hold | george clooney | \ | Easy | 0 | 53 |  | High
ENHC0014930 | 2023-11-02 | 2024-08-30 | steven | Daniel | 32054 | User Story | Tuesday, April 9, 2024 |  | Modify Service Desk dashboards | Closed | larry wilmore | \Dahlia | Easy | 0 | 5 |  | Low
ENHC0014930 | 2023-11-02 | 2024-08-30 | steven | Lukas | 34220 | User Story | Monday, October 7, 2024 |  | Service Desk cross training | New | larry wilmore | \ | Easy | 36 | 38 |  | Low
ENHC0014930 | 2023-11-02 | 2024-08-30 | steven | Daniel | 33578 | User Story | Thursday, August 29, 2024 |  | Fix / enhance Service Desk dashboards | Active | james murray | \Poppy | Easy | 10 | 1 |  | Low
ENHC0014930 | 2023-11-02 | 2024-08-30 | steven | Connor | 30022 | Feature | Thursday, November 2, 2023 | Service Desk dashboards |  | Active | jake from statefarm | \ | Medium | 53 | 17 | Sunday, May 12, 2024 | Low
ENHC0014828 | 2023-07-19 | 2024-09-19 | mel | Lukas | 29038 | Feature | Wednesday, July 19, 2023 | FCR (fist contact resolution) Service now report and power BI dashboard. |  | New | jake from statefarm | \ | Easy | 5 | 79 |  | High
ENHC0015035 | 2024-01-31 | 2024-10-17 | mel | Lukas | 32308 | User Story | Wednesday, May 1, 2024 |  | Get requirements / scope | New | michelle obama | \ | Easy | 38 | 4 |  | Low
ENHC0015035 | 2024-01-31 | 2024-10-17 | harry | Connor | 31125 | Feature | Wednesday, January 31, 2024 | Controls project |  | On Hold | larry wilmore | \ | Easy | 17 | 42 |  | Low
ENHC0015409 | 2024-10-14 | 2024-10-14 | mel | Lukas | 34334 | Feature | Monday, October 14, 2024 | PowerBI query from Finance Source |  | New | lawrence taylor | \ | Hard | 79 | 58 |  | Low
ENHC0015326 | 2024-09-19 | 2024-09-19 | anthony | Lukas | 33880 | Feature | Thursday, September 19, 2024 | Updates to Concession Incentive Program |  | New | lawrence taylor | \ | Easy | 4 | 31 |  | Low
ENHC0015247 | 2024-07-03 | 2024-10-17 | mel | Lukas | 32907 | Feature | Wednesday, July 3, 2024 | Concessions gross sales report - ADA compliant |  | On Hold | lawrence taylor | \ | Easy | 42 | 1 |  | High
ENHC0015170 | 2024-05-08 | 2024-09-19 | mel | Lukas | 32363 | Feature | Wednesday, May 8, 2024 | Parking - Lost and Found Dashboard |  | New | mark cuban | \ | Medium | 58 | 65 |  | Low
ENHC0015428 | 2024-10-22 | 2024-10-22 | mel | Lukas | 34436 | Feature | Tuesday, October 22, 2024 | In the Service Request Data Warehouse, need the "SENT TO" field created |  | New | matthew broderick | \ | Easy | 31 | 41 |  | Low
ENHC0015191 | 2024-05-23 | 2024-10-08 | mel | Lukas | 32552 | User Story | Friday, May 31, 2024 |  | Test connectivity to LogPlan Server | Closed | lawrence taylor | \Daffodil | Easy | 1 | 57 |  | Low
ENHC0015191 | 2024-05-23 | 2024-10-08 | harry | Connor | 32670 | User Story | Wednesday, June 12, 2024 |  | Extract, transform and load data | Awaiting Customer | bryan adams | \ | Medium | 65 | 35 |  | Low
ENHC0015191 | 2024-05-23 | 2024-10-08 | mel | Lukas | 32519 | Feature | Thursday, May 23, 2024 | Baggage Handling System data into the DEN Data Warehouse |  | On Hold | matthew broderick | \ | Easy | 41 | 11 |  | High
ENHC0014906 | 2023-10-04 | 2024-09-19 | harry | Connor | 31596 | Feature | Friday, March 1, 2024 | New measure for train system |  | New | matthew broderick | \ | Medium | 57 | 46 |  | High
ENHC0015314 | 2024-09-09 | 2024-10-17 | mary | Daniel | 34114 | User Story | Monday, September 30, 2024 |  | Workflow data Integration from Crisis Management Software Workflow | On Hold | robert downey | \ | Easy | 40 | 10 |  | Low
ENHC0015314 | 2024-09-09 | 2024-10-17 | mary | Daniel | 33706 | Feature | Monday, September 9, 2024 | Crisis Management Workflow API Call Proof of Concept/Documentation |  | On Hold | michael myers | \Lavender | Easy | 35 | 82 |  | High
ENHC0015165 | 2024-05-03 | 2024-10-17 | anthony | Daniel | 32419 | User Story | Tuesday, May 14, 2024 |  | Update report | Deployment | travis barker | \ | Easy | 11 | 91 |  | Low
ENHC0015165 | 2024-05-03 | 2024-10-17 | anthony | Lukas | 32323 | Feature | Friday, May 3, 2024 | Update SSRS Business Directory Report to be ADA Complaint. |  | On Hold | michelle obama | \ | Easy | 46 | 0 |  | Low
ENHC0015126 | 2024-04-10 | 2024-09-19 | rachel | Daniel | 32314 | User Story | Wednesday, May 1, 2024 |  | Architecture | Closed | lawrence taylor | \Zinnia | Hard | 82 | 14 |  | Low
ENHC0015126 | 2024-04-10 | 2024-09-19 | rachel | Daniel | 34459 | User Story | Wednesday, October 23, 2024 |  | Deploy Data Gateway | On Hold | rebecca demornay | \Poppy | Hard | 91 | 99 |  | Low
ENHC0015126 | 2024-04-10 | 2024-09-19 | rachel | Daniel | 34117 | User Story | Monday, September 30, 2024 |  | SSIS integration from Sharepoint to data gateway | Closed | george clooney | \Zinnia | Easy | 16 | 20 |  | Low
ENHC0015126 | 2024-04-10 | 2024-09-19 | rachel | Lukas | 32064 | Feature | Wednesday, April 10, 2024 | Procurement Opportunities to Flydenver API Gateway |  | Active | michelle obama | \ | Easy | 0 | 53 |  | Low
ENHC0015114 | 2024-03-26 | 2024-10-08 | anthony | Daniel | 31892 | User Story | Wednesday, March 27, 2024 |  | Create integration for people counter report | Closed | michael keaton | \Sunflower | Easy | 14 | 12 |  | Low
ENHC0015114 | 2024-03-26 | 2024-10-08 | anthony | Connor | 32620 | User Story | Thursday, June 6, 2024 |  | Create tabular model for people counter | Closed | matthew broderick | \Jasmine | Hard | 99 | 42 |  | Low
ENHC0015114 | 2024-03-26 | 2024-10-08 | anthony | Lukas | 32837 | User Story | Thursday, June 27, 2024 |  | Create dashboard for people counters | Closed | nate bargatze | \Jasmine | Medium | 53 | 84 |  | Low
ENHC0015114 | 2024-03-26 | 2024-10-08 | anthony | Daniel | 31884 | Feature | Tuesday, March 26, 2024 | Create platform people counter report |  | On Hold | nate bargatze | \ | Easy | 12 | 75 |  | Low
ENHC0015451 | 2024-10-31 | 2024-10-31 | steven | Connor | 34588 | Feature | Thursday, October 31, 2024 | Products data cleanup |  | Active | lonnie anderson | \Poppy | Easy | 42 | 68 |  | Low
ENHC0015450 | 2024-10-31 | 2024-10-31 | steven | Lukas | 34587 | Feature | Thursday, October 31, 2024 | Insurance data to Power BI |  | Active | derek henry | \Poppy | Hard | 84 | 6 |  | Low
ENHC0015449 | 2024-10-31 | 2024-10-31 | steven | Connor | 34586 | Feature | Thursday, October 31, 2024 | Load Screening Q3 data |  | Active | james murray | \Poppy | Medium | 75 | 68 |  | Low
ENHC0015048 | 2024-02-08 | 2024-09-19 | steven | Lukas | 32168 | User Story | Wednesday, April 17, 2024 |  | Create a list of solutions | New | mark cuban | \ | Medium | 68 | 47 |  | Low
ENHC0015048 | 2024-02-08 | 2024-09-19 | steven | Daniel | 31264 | Feature | Thursday, February 8, 2024 | Connectors Migration |  | New | rebecca demornay | \ | Easy | 6 | 3 |  | Low
ENHC0015410 | 2024-10-15 | 2024-10-30 | harry | Connor | 34347 | Feature | Tuesday, October 15, 2024 | Add a field to the Employee Extract file in the Database |  | New | renee zellwegger | \ | Medium | 68 | 76 |  | High
ENHC0015258 | 2024-07-16 | 2024-09-27 | mel | Connor | 34168 | User Story | Wednesday, October 2, 2024 |  | Gather Fuel requirements | New | michael keaton | \Poppy | Easy | 2 | 0 |  | Low
ENHC0015258 | 2024-07-16 | 2024-09-27 | mel | Daniel | 33013 | Feature | Tuesday, July 16, 2024 | Add Search for the Fuel form and process |  | New | steve martin | \ | Easy | 47 | 52 |  | Low
ENHC0015044 | 2024-02-05 | 2024-09-19 | harry | Lukas | 31231 | Feature | Monday, February 5, 2024 | DEN Commercial Dashboard 2.0 |  | New | tina fey | \ | Easy | 3 | 78 |  | High
ENHC0015195 | 2024-05-29 | 2024-10-25 | steven | Daniel | 32631 | User Story | Monday, June 10, 2024 |  | Rob to look at the data integration API | Closed | renee zellwegger | \ | Hard | 76 | 15 |  | Low
ENHC0015195 | 2024-05-29 | 2024-10-25 | steven | Daniel | 34653 | User Story | Wednesday, November 6, 2024 |  | Develop SSIS integration | Active | lawrence taylor | \Poppy | Easy | 10 | 20 |  | Low
ENHC0015195 | 2024-05-29 | 2024-10-25 | steven | Lukas | 33275 | User Story | Monday, August 5, 2024 |  | Gathering requirements | Closed | lawrence taylor | \Lavender | Medium | 52 | 4 |  | Low
ENHC0015195 | 2024-05-29 | 2024-10-25 | steven | Connor | 34517 | User Story | Thursday, October 24, 2024 |  | Expand people counter data | Closed | derek henry | \Poppy | Easy | 5 | 5 |  | Low
ENHC0015195 | 2024-05-29 | 2024-10-25 | steven | Connor | 32531 | Feature | Wednesday, May 29, 2024 | Expanding the data that is being passed to us from People counter source via API |  | Active | tracy chapman | \ | Hard | 78 | 99 |  | High
ENHC0015091 | 2024-03-08 | 2024-03-08 | harry | Connor | 31651 | Feature | Friday, March 8, 2024 | OPs Security Screening Occupancy Reporting |  | New | tracy chapman | \ | Easy | 15 | 58 |  | Low
ENHC0015078 | 2024-03-01 | 2024-09-19 | harry | Connor | 32436 | User Story | Friday, May 17, 2024 |  | Outbound Phone calls vendor 1 - update dashboard | Closed | eliot page | \Sunflower | Easy | 20 | 23 |  | Low
ENHC0015078 | 2024-03-01 | 2024-09-19 | harry | Daniel | 32438 | User Story | Friday, May 17, 2024 |  | Airport Alarms (update dashboards) | Closed | branden flowers | \Hydrangea | Hard | 99 | 79 |  | Low
ENHC0015078 | 2024-03-01 | 2024-09-19 | mel | Connor | 32439 | User Story | Friday, May 17, 2024 |  | Notification System - integration design | Active | jake from statefarm | \Poppy | Medium | 58 | 13 |  | Low
ENHC0015078 | 2024-03-01 | 2024-09-19 | harry | Connor | 32440 | User Story | Friday, May 17, 2024 |  | Notification System - SSIS development | New | chelesa clinton | \Carnation | Easy | 23 | 85 |  | Low
ENHC0015078 | 2024-03-01 | 2024-09-19 | mel | Connor | 32441 | User Story | Friday, May 17, 2024 |  | Notification System - Tabular model development | New | george clooney | \Carnation | Hard | 79 | 48 |  | Low
ENHC0015078 | 2024-03-01 | 2024-09-19 | harry | Connor | 32442 | User Story | Friday, May 17, 2024 |  | Notification System - create dashboard | New | michael douglas | \Carnation | Easy | 13 | 49 |  | Low
ENHC0015078 | 2024-03-01 | 2024-09-19 | mel | Connor | 32443 | User Story | Friday, May 17, 2024 |  | Radio calls - update dashboard | On Hold | lonnie anderson | \ | Hard | 85 | 69 |  | Low
ENHC0015078 | 2024-03-01 | 2024-09-19 | harry | Lukas | 32444 | User Story | Friday, May 17, 2024 |  | Crisis Management Software Log Book Entries - requirements | New | derek henry | \ | Easy | 48 | 41 |  | Low
ENHC0015078 | 2024-03-01 | 2024-09-19 | harry | Daniel | 32445 | User Story | Friday, May 17, 2024 |  | Crisis Management Software Parking Log Items | Closed | robert downey | \Hydrangea | Easy | 49 | 35 |  | Low
ENHC0015078 | 2024-03-01 | 2024-09-19 | mel | Connor | 32446 | User Story | Friday, May 17, 2024 |  | Teams interactions - requirements | On Hold | rebecca demornay | \ | Medium | 69 | 64 |  | Low
ENHC0015078 | 2024-03-01 | 2024-09-19 | harry | Connor | 33440 | User Story | Tuesday, August 20, 2024 |  | Single data model - Phone Calls data from Vendor 1 and 2 | Closed | russell peters | \Hydrangea | Easy | 41 | 95 |  | Low
ENHC0015078 | 2024-03-01 | 2024-09-19 | harry | Daniel | 32437 | User Story | Friday, May 17, 2024 |  | Phone Calls Vendor 2 - update dashboard | Active | bryan adams | \Poppy | Easy | 8 | 16 |  | Low
ENHC0015078 | 2024-03-01 | 2024-09-19 | mel | Connor | 31603 | Feature | Friday, March 1, 2024 | Comms Center Dashboard |  | Active | tracy chapman | \ | Easy | 35 | 69 |  | High
ENHC0015069 | 2024-02-26 | 2024-09-19 | mel | Daniel | 31483 | Feature | Monday, February 26, 2024 | Update to Maintenance database |  | New | tracy chapman | \ | Medium | 64 | 94 |  | Low
ENHC0015051 | 2024-02-09 | 2024-09-19 | harry | Lukas | 31266 | Feature | Friday, February 9, 2024 | Connect to an external weather dataset for our Snow Dashboards probably via API to help our team better tell the story about runway downtime. |  | New | tracy chapman | \ | Hard | 95 | 0 |  | Low
ENHC0015259 | 2024-07-16 | 2024-09-19 | mel | Connor | 33034 | Feature | Tuesday, July 16, 2024 | Non-Production Network Production/Inventory Values and Cost Estimation sheets need adjusting/correcting (use attached docs) |  | New | travis barker | \ | Medium | 69 | 50 |  | Low